## Decision Log & RACI
Packers & Movers Platform - Asynchronous Decision Log & RACI Matrix
Asynchronous Roadmap Review Framework & Stakeholder Feedback Tracking
Feedback ID | Stakeholder & Role | Roadmap Epic / Feature | Stakeholder Input / Concern | PM Decision & Resolution | RACI Role | Status
FB-01 | Operations Lead | 1-Day Advance Booking | Operational capacity risks during weekend surges. | Accepted: Cap short-notice bookings at 20% of daily fleet capacity for Quarter 1 MVP. | Responsible | Resolved
FB-02 | Legal Counsel | Damage Compensation Guarantee | Financial risk without pre-move inventory inspection. | Deferred: Require mandatory pre-move item condition checklist in Quarter 2 (Release 1). | Consulted | In Review
FB-03 | Growth Lead | 200% Growth Goal | Requires built-in referral incentive. | Accepted: Add promo code field to Quarter 1 MVP booking engine. | Accountable | Resolved
FB-04 | Engineering Lead | Real-Time GPS Tracking | High telemetry server load and latency risk during move day. | Accepted: Implement milestone-based status updates for MVP; roll out live map telemetry in Release 1. | Responsible | Resolved